## Task Management
Task ID | Project ID | Task Name | Start Date | End Date | Assigned To | Progress (%) | Issues
T001 | P001 | Surface Preparation | 2025-01-02 | 2025-01-05 | Manager A | 50 | None
T002 | P001 | Primer Application | 2025-01-10 | 2025-01-15 | Manager B | 30 | Delay in material
T003 | P002 | Final Coating | 2025-02-16 | 2025-02-20 | Manager A | 0 | Pending Approval
T004 | P002 | Inspection | 2025-03-01 | 2025-03-05 | Manager C | 0 | Not Started
T005 | P003 | Inspection | 2025-03-02 | 2025-03-06 | Manager C | 0 | Not Started
T006 | P004 | Final Coating | 2025-03-03 | 2025-03-07 | Manager D | 30 | Not Started

## Resource Allocation
Employee ID | Employee Name | Role | Project ID | Task Assigned | Hours Allocated
E001 | sanjay | Supervisor | P001 | Surface Preparation | 20
E002 | Bob | Technician | P001 | Primer Application | 30
E003 | Charlie | Painter | P002 | Final Coating | 25
E004 | David | Inspector | P002 | Inspection | 15
E005 | sam | manager | P003 | managinf | 19
E006 | kumar | painter | P002 | Final Coating | 26

## Costing & Budgeting
Project ID | Estimated Cost | Actual Cost | Material Cost | Labor Cost | Variance | Status
P003 | 500000 | 250000 | 100000 | 150000 | 250000 | On Budget
P002 | 750000 | 0 | 0 | 0 | 750000 | Pending Start
P002 | 63888 | 3 | 1000000 | 200000 | 640000 | On Budget

## Progress Tracking
Project ID | Milestones Completed | Open Issues | Delays (Days) | Risk Level | Overall Status
P001 | 2 | 1 | 5 | Medium | On Track
P002 | 0 | 1 | 0 | Low | Pending Start

## Dashboard
Project ID | Completion (%) | Open Issues | Budget Status | Overall Status
P001 | 40 | 1 | On Budget | On Track
P002 | 0 | 1 | Pending Start | Pending Start