## Task Management
Task ID | Project ID | Task Name | Start Date | End Date | Assigned To | Progress (%) | Issues
T001 | P001 | Surface Preparation | 2025-01-02 | 2025-01-05 | Manager A | 50 | None
T002 | P001 | Primer Application | 2025-01-10 | 2025-01-15 | Manager B | 30 | Delay in material
T003 | P002 | Final Coating | 2025-02-16 | 2025-02-20 | Manager A | 0 | Pending Approval
T004 | P002 | Inspection | 2025-03-01 | 2025-03-05 | Manager C | 0 | Not Started

## Resource Allocation
Employee ID | Employee Name | Role | Project ID | Task Assigned | Hours Allocated
E001 | Alice | Supervisor | P001 | Surface Preparation | 20
E002 | Bob | Technician | P001 | Primer Application | 30
E003 | Charlie | Painter | P002 | Final Coating | 25
E004 | David | Inspector | P002 | Inspection | 15

## Material Tracking
Material ID | Material Name | Project ID | Quantity Required | Quantity Used | Supplier | Status
M001 | Primer | P001 | 50 | 25 | Supplier A | In Stock
M002 | Coating Paint | P001 | 100 | 40 | Supplier B | Partial Usage
M003 | Sealer | P002 | 75 | 0 | Supplier C | Not Delivered

## Costing & Budgeting
Project ID | Estimated Cost | Actual Cost | Material Cost | Labor Cost | Variance | Status
P001 | 500000 | 250000 | 100000 | 150000 | 250000 | On Budget
P002 | 750000 | 0 | 0 | 0 | 750000 | Pending Start

## Progress Tracking
Project ID | Milestones Completed | Open Issues | Delays (Days) | Risk Level | Overall Status
P001 | 2 | 1 | 5 | Medium | On Track
P002 | 0 | 1 | 0 | Low | Pending Start

## Dashboard
Project ID | Completion (%) | Open Issues | Budget Status | Overall Status
P001 | 40 | 1 | On Budget | On Track
P002 | 0 | 1 | Pending Start | Pending Start